## Sheet1
Meetings # | Meeting Type | Day | Time | Attendees | Topics | Planned Tasks | Location
1 | Standup | 2017-10-23 | 15 minutes | All | Planning Development | Decide on an idea and plan meetings | Eaton
2 | Online | 2017-10-24 | 30 minutes | Alex, Jakob, Quinten | Planning Development and Tasks | Create task list and things people can work on | Discord
3 | Standup | 2017-10-27 | 45 minutes | All | Setting Up Access & Learning Unity & Blender | Unity, Blender, and HacknPlan Setup & Tasks | Eaton / Spahr
4 | Code Session | 2017-10-30 | 1 hour + | Alex, Jakob, Austin | Buoyancy, Water, AI, Checkpoints | Finish New Water Sys, AI Movement, Player Can Win | Anchutz
5 | Code Session | 2017-11-01 | 2 hours | All | Powerups, Obstacles, AI, Water, Menu | Menu & Scene Selection, Buoyancy Implementation, Pathfinding | Anchutz
6 | Standup | 2017-11-03 | 15 minutes | All | Tasks Left, Meetup, Delegation | Everyone has job | Eaton
7 | Code Session | 2017-11-03 | 2 hours | All | Movement of Whale, AI Pathfinding, Underwater | Implement all systems into one & Underwater Graphics/Movement | Eaton / Online
8 | Code Session | 2017-11-04 | 8 hours | All | Clean Movement, Buoyancy of Objs, Improved Pathfinding | More Advanced AI, Better Water System Implemented | Austin's House
9 | Online | 2017-11-05 | 5 hours | All | AI touchup, Obstacles/Powerups, Race Mechanics | Make game run smooth and fun, fix bugs | Online
10 | Slack/Discord | 2017-11-07 | 1 hour | All | Demo Touch-up, Bugfixing | Fix water bugs and ai | Anchutz
11 | In-Person/Standup | 2017-11-10 | 2 hours | All | Handing Out Jobs, Whiteboarding | Debriefing and Planning | EECS Lab
12 | Online/Discord | 2017-11-11 | 2 hours | Alex, Rohan, Quinten, Jakob | Water Shading, Movement, Map Pickups | Perfect water and displacement, buoyancy, object interaction and placemtn | Online
13 | Code Session | 2017-11-14 | 1 hour | All | Movement, Menu, Underwater, AI | Smooth overwater movement, Fix Underwater, AI Improve Nav | Anchutz
14 | Online | 2017-11-16 | 1 hour | All | Underwater Movement, Visuals, Splitscreen | Movement Flow Over and Underwater & Splitscreen Base | Online
15 | Code Session | 2017-11-17 | 2 hours | All | Movement and Pickup Touchup, LAN Connection | Game Works On LAN Multiplayer | EECS Lab
16 | Online/Discord | 2017-11-18 | 4 hours | All | Shipyard Map, Visual and Sound Mashup, LAN Smooth | Add New Map, Add LAN Support | Online
17 | Standup/Online | 2017-11-20 | 1 hour 15 min | All | Minefield Map, Smooth LAN Setup, Multi-Player Capability | Add Muliplayer LAN, New Map, and Smooth Out Moving Networked | Online / In-Class
18 | Online | 2017-11-21 | 2 hours | All | Sound SFX, Splitscreen Multiple Maps, Health | Incorporate Features into All maps, Add Sound Features | Online
19 | Online Meetup | 2017-11-24 | 4 hours | Austin, Jakob, Rohan, Alex | Sound Touchup, LAN Multi Maps, Minimap | Add LAN to all maps, Bugfix Sound, Displacement Shader To All Whales | Online
20 | Online/Discord | 2017-11-25 | 6 hours | Austin, Rohan, Jakob | GUI Elements, Speed, and Small Movement Parts | Incorporate Pieces and Parts For User Experience | Online
21 | Online/Discord | 2017-11-26 | 5 hours | All | Create Tests, Adjust any water bugs and movement | Test Suite, User Experience Feels Right, and Deployed Version Works | Online
22 | Online/Discord | 2017-11-28 | 4 hours | Alex, Jakob, Rohan, Quinten | Sound Option Menu, Blowhole Sound, LAN, Map Incorporation | Incorporate Audio Mixer To Connect Sounds, Fix Errors in Maps | Online
23 | Standup/Online | 2017-11-29 | 6 hours | All | Testing LAN, MP, and Maps | Talked About What's Left, Bugfixing, Testing Phase | Online
24 | Online/Discord | 2017-11-29 | 6 hours | All | Finishing Touches and Network Support | Finish Game, Fix Bugs, Touch-up Before Midnight | Online